FITNESS SAAS PLATFORM

Solo Founder Execution Blueprint

Phase 0 → MVP Sprint Plan

Budget: ₹50 Lakhs  |  Timeline: 9 Months  |  Team: Founder + 2 Contract Developers

| Phase 0-1 Foundations Weeks 1–9 ₹7.5L | Phase 2-3 Core MVP + Billing Weeks 10–23 ₹13L | Phase 4-5 WhatsApp + Biometrics Weeks 24–34 ₹10L | Launch Pilot + GTM Weeks 35–39 ₹5L |
| --- | --- | --- | --- |

# 1. Solo Founder Reality Check

Before sprinting, you need an unambiguous view of what ₹50 Lakhs buys, what it does not buy, and the single highest-risk decision you face in Month 1.

## 1.1 What ₹50 Lakhs Buys

At current Indian contractor market rates, your budget covers approximately 9 months of focused development with a lean 3-person team (you + 2 contract developers). This is enough to build a credible, sellable MVP — not a feature-complete product.

| Full-time contract devs | 2 developers for 8 months (1 senior full-stack, 1 mid-level frontend) |
| --- | --- |
| AWS infrastructure | Multi-tenant Postgres, Redis, SQS, S3 — MVP scale config |
| 3rd-party integrations | 1 UPI gateway (Razorpay), 1 WhatsApp BSP, 1 biometric path (eSSL) |
| Legal + compliance | Company registration, basic contracts, GST registration |
| Pre-launch GTM | 1 trade show booth (IHFF), outbound tools, pilot gym onboarding |
| Founder runway | Personal expenses for 10-12 months at modest draw |
| Contingency | ~₹5L buffer for delays, scope changes, and unexpected licensing costs |

## 1.2 What It Does Not Buy

- An in-house team. You cannot afford salaried employees with PF, benefits, and notice periods.

- Multiple payment gateway integrations at launch. Pick one and own it.

- The full ML retention engine. That is a Month 7+ problem. Rules-based churn scoring ships first.

- Enterprise multi-location support at MVP. Target single-location gyms first.

- A dedicated DevOps engineer. You will use managed services heavily to compensate.

## 1.3 Your Single Most Important Month 1 Decision

| CRITICAL | You must decide whether to hire a technical co-founder (equity) or rely entirely on contractors (cash). A co-founder costs you 15-25% equity but removes architectural risk and saves ₹8-12L in contractor fees. A contractor team is faster to start but slower to align on vision. This decision cannot be undone easily. Make it before writing a single line of code. |
| --- | --- |

# 2. Hiring Strategy for Phase 0→MVP

## 2.1 The Minimum Viable Team

You need exactly three capabilities: architecture + backend, frontend + mobile-first UI, and DevOps-lite. As the founder, you own product, sales, and integration decisions. Hire the other two as contractors.

| Founder (You) | Product decisions, BSP/gateway vendor negotiations, pilot gym relationships, sprint planning, QA sign-off |
| --- | --- |
| Senior Full-Stack Dev | Backend API, database schema, multi-tenant architecture, payment + WhatsApp integrations, biometric API. Target: 4+ years, Node.js or Go, PostgreSQL, AWS. Rate: ₹70K–1.1L/month |
| Mid Frontend Dev | React admin dashboard, member-facing PWA, mobile-first design system, form workflows. Target: 3+ years React, Tailwind, REST API consumption. Rate: ₹50K–75K/month |

## 2.2 Where to Hire

- Toptal / Turing: Pre-vetted, expensive (₹1.2–1.5L/month), but zero screening time. Use for the senior dev if you cannot afford 2 weeks of interviews.

- LinkedIn + Internshala: 2-3 week sourcing cycle, but access to strong mid-career contractors at better rates.

- Referrals: If you know anyone in the Bangalore / Pune startup ecosystem, a warm referral for a contract dev is worth 3 weeks of LinkedIn sourcing.

- Avoid agencies for core development: Fixed-price agencies create waterfall-style deliverables that are misaligned with iterative SaaS development.

## 2.3 Contract Structure

- Use milestone-based contracts, not hourly billing. Pay on delivery of sprint goals, not hours logged.

- Weekly 1-hour sprint reviews via video call are non-negotiable. Async-only teams drift.

- Retain source code ownership explicitly in the contract. Use a standard IP assignment clause.

- 3-month initial term with renewal. Do not sign 12-month contracts with contractors you have not yet validated.

# 3. Full Budget Breakdown (₹50 Lakhs)

Every rupee is allocated below. The contingency line is real money — do not treat it as slack.

| Category | Item | Amount (INR) |
| --- | --- | --- |
| TEAM | Senior Full-Stack Dev (8 months × ₹90K avg) | ₹7,20,000 |
| TEAM | Mid Frontend Dev (6 months × ₹62K avg) | ₹3,72,000 |
| TEAM | Founder Draw (10 months × ₹75K) | ₹7,50,000 |
| INFRASTRUCTURE | AWS (EC2, RDS Postgres, Redis, S3, SQS) — 9 months | ₹2,70,000 |
| INFRASTRUCTURE | GitHub, CI/CD (GitHub Actions), monitoring tools | ₹30,000 |
| INTEGRATIONS | Razorpay setup + transaction fees reserve | ₹50,000 |
| INTEGRATIONS | WhatsApp BSP (AiSensy / WAPI — 12 months) | ₹12,000 |
| INTEGRATIONS | eSSL ADMS cloud hosting (50 users, 2 devices) | ₹24,000 |
| INTEGRATIONS | Meta conversation costs reserve (business-initiated) | ₹20,000 |
| LEGAL | Company registration, contracts, GST setup | ₹75,000 |
| LEGAL | IP assignment agreements, NDA templates | ₹15,000 |
| DESIGN | Figma Pro + UI asset licenses (12 months) | ₹24,000 |
| GTM — PRE-LAUNCH | IHFF trade show booth (1 city, basic setup) | ₹1,50,000 |
| GTM — PRE-LAUNCH | Outbound sales tools (LinkedIn Sales Nav, CRM) | ₹60,000 |
| GTM — PRE-LAUNCH | Demo hardware (1 eSSL device + RFID reader) | ₹18,000 |
| GTM — PRE-LAUNCH | Content, SEO, WhatsApp group community building | ₹40,000 |
| CONTINGENCY | Delays, scope creep, additional API licensing | ₹5,00,000 |
| TOTAL ALLOCATED |  | ₹51,30,000 |

| NOTE | The budget is tight but executable. The two largest line items — team and founder draw — total ₹18.4L. If you find a technical co-founder willing to work for equity, those ₹18.4L become additional runway, de-risking the entire plan significantly. |
| --- | --- |

# 4. Phase-by-Phase Sprint Plan

| PHASE 0 Architecture + Economics Decisions | TIMELINE Weeks 1–3 | BUDGET ₹1.2L |
| --- | --- | --- |

This phase costs almost nothing in development but is the highest-leverage 3 weeks of the entire project. Decisions made here determine your margin structure, your hiring spec, and your first pilot gym's onboarding experience.

Deliverables

- Tenant class definitions (SMB / Mid / Enterprise) with routing rules documented

- BSP selection matrix completed with a primary and fallback WhatsApp provider chosen

- Usage Ledger schema draft: billable events, metering fields, overage rules per tier

- ML staging timeline committed: rules-based launch, cohort baseline at Month 4, model at Month 8

- Data provenance tagging spec: source_system, imported_at, confidence_level fields defined

- Canonical domain model finalized: members, plans, contracts, invoices, payments, attendance, devices

- AWS account setup, IaC skeleton (Terraform), and environment parity (dev / staging / prod)

- Contractor hiring started: job spec posted, first interviews scheduled

BSP Selection Criteria (Decide This Week)

| Template Approval SLA | How many days for initial approval and re-approval on template edits? |
| --- | --- |
| Meta markup on fees | 0% markup BSPs (WAPI, BOL7) save ₹3-8K/month vs marked-up providers at scale |
| Multi-tenant WABA isolation | Can each gym tenant operate under their own WhatsApp number? |
| Webhook delivery SLA | What is the guaranteed message delivery latency and failure rate? |
| BSP portability | How painful is migrating templates and WABA to a new provider? |

Exit Criteria

| EXIT | All architectural decisions are documented in a single Architecture Decision Record. Hiring pipeline is live. AWS environments are provisioned. You can articulate your pricing-to-cost model for WhatsApp and biometrics in one page. |
| --- | --- |

| PHASE 1 Platform Foundations | TIMELINE Weeks 4–9 | BUDGET ₹6.3L |
| --- | --- | --- |

Developers join in Week 4. This phase builds the secure, observable infrastructure that every future feature depends on. Nothing customer-facing ships yet.

Sprint Breakdown

| Sprint / Week | Goal | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Weeks 4–5 | Repo + CI/CD + Auth | Mono-repo, GitHub Actions pipeline, JWT auth, RBAC skeleton, tenant isolation with RLS | Any tenant-scoped API call enforces isolation |
| Weeks 6–7 | Core data model + event bus | Postgres schema, event outbox, SQS/RabbitMQ wired, audit log table | Every write emits an event with tenant_id |
| Weeks 8–9 | Usage Ledger + UI shell | Usage ledger schema live, billable event capture wired, React admin shell with design system | Any billable action writes to ledger and is queryable |

Exit Criteria

| EXIT | Secure multi-tenant skeleton deployed to staging. Any entity can be created and read end-to-end with audit logs and usage events captured. CI/CD deploys on every push to main. |
| --- | --- |

| PHASE 2 Core Operations MVP | TIMELINE Weeks 10–17 | BUDGET ₹8.5L |
| --- | --- | --- |

The first shippable product. After Week 17, a real gym front desk can run daily operations without spreadsheets. This is your proof-of-concept for the first pilot gym.

Sprint Breakdown

| Sprint / Week | Goal | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Weeks 10–11 | Member lifecycle | Onboarding form, plan assignment, member profile, freeze/upgrade/transfer workflows | Member can be enrolled and plan assigned in under 3 minutes |
| Weeks 12–13 | Scheduling + capacity | Class schedule builder, capacity limits, basic slot booking, attendance manual entry | Class can be created and members booked against capacity |
| Weeks 14–15 | Billing + invoicing | Invoice generation, manual payment recording, refunds, adjustment notes | Invoice generated on plan assignment with correct GST line items |
| Weeks 16–17 | Staff + POS lite | Staff roles, task tracking, commission rules, add-on product sales at front desk | Front desk can process a walk-in sale and log a trainer commission |

Pilot Gym Target

By Week 16, you should have one pilot gym operator using this system for real daily operations. This is not a demo — it is production use. Their feedback in Weeks 16-17 directly shapes Phase 3 prioritization.

- Offer 3 months free in exchange for weekly feedback calls and permission to reference them in sales.

- Choose a gym with 200-500 members and 2-3 front desk staff. Complex enough to stress-test, small enough to manage.

- Be physically present for their first week of onboarding. You will learn more in 3 days than in 3 weeks of remote feedback.

Exit Criteria

| EXIT | One pilot gym is running daily operations on the platform. Front desk staff can complete member enrollment, plan assignment, and manual payment recording without your help. Zero critical bugs in production for 5 consecutive days. |
| --- | --- |

| PHASE 3 Payments + GST Engine | TIMELINE Weeks 18–23 | BUDGET ₹4.5L |
| --- | --- | --- |

This phase transforms the platform from a ledger into a revenue engine. UPI collection, automated invoicing, and e-NACH recurring payments unlock the core value proposition for gym owners.

Sprint Breakdown

| Sprint / Week | Goal | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Weeks 18–19 | Razorpay UPI integration | UPI QR generation at front desk, payment link collection, webhook reconciliation | Member can pay via UPI and invoice marks as paid automatically |
| Weeks 20–21 | GST engine | Service vs product tax differentiation, dynamic GST calculation, Tally-export format | Invoice includes correct CGST/SGST with HSN code and is export-ready |
| Weeks 22–23 | Usage billing + overages | Tier-based quotas wired to usage ledger, overage calculation, invoice line items for pass-through costs | WhatsApp and biometric costs appear on tenant invoices where applicable |

Critical Decision: e-NACH

| NOTE | e-NACH (auto-debit mandate) for recurring subscriptions requires RBI-registered payment aggregator approval and 2-4 weeks of bank onboarding. Begin the Razorpay e-NACH application in Week 18 in parallel with development — it will not be ready in time if you wait. |
| --- | --- |

Exit Criteria

| EXIT | 95% of test transactions succeed end-to-end. Invoices generate automatically on payment and include correct GST. Usage ledger costs appear on tenant billing statements. Pilot gym is processing real UPI payments. |
| --- | --- |

| PHASE 4 WhatsApp Communications Platform | TIMELINE Weeks 24–29 | BUDGET ₹4.8L |
| --- | --- | --- |

This is the feature that will close the majority of your sales demos. When a gym owner sees an automated renewal nudge fire with a UPI payment link embedded, the sale is almost done.

Sprint Breakdown

| Sprint / Week | Goal | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Weeks 24–25 | BSP integration + templates | BSP API wired, opt-in consent management, first 5 approved templates (renewal, receipt, booking confirmation, class reminder, welcome) | Template message sends successfully with delivery receipt captured |
| Weeks 26–27 | Workflow engine | Renewal nudge sequences (T-7, T-3, T-0 days), payment failure follow-up, class reminder automation | Renewal nudge fires automatically with embedded UPI link 7 days before expiry |
| Weeks 28–29 | Metering + cost control | Conversation cost tracking in usage ledger, tier-based throttling, tenant budget alerts, delivery reporting dashboard | WhatsApp cost per tenant is visible and invoiced correctly |

Template Pre-Registration Strategy

Meta template approval can take 2-7 business days and templates are sometimes rejected for policy reasons. Prepare the following templates in Week 23 before development begins:

- Membership renewal reminder (utility template)

- Payment confirmation receipt (utility template)

- Class booking confirmation (utility template)

- Welcome message on enrollment (utility template)

- Promotional offer broadcast (marketing template — prepare but do not rely on immediate approval)

Exit Criteria

| EXIT | Renewal automation is live on the pilot gym and showing measurable uplift vs. manual follow-up. WhatsApp costs appear in usage ledger and tenant billing. Delivery rate above 92% for utility messages. |
| --- | --- |

| PHASE 5 Biometric Access Control (eSSL) | TIMELINE Weeks 30–35 | BUDGET ₹3.8L |
| --- | --- | --- |

One integration path only at MVP. eSSL is the most widely deployed biometric hardware brand in Indian gyms and the most practical first target. ZkTeco and Matrix are Phase 9 additions.

Sprint Breakdown

| Sprint / Week | Goal | Key Deliverables | Exit Criteria |
| --- | --- | --- | --- |
| Weeks 30–31 | Device registry + health monitoring | Device registration in SaaS, heartbeat polling, online/offline status, sync failure alerting to gym admin | Gym admin can see device status and last successful sync time |
| Weeks 32–33 | eSSL ADMS integration | eSSL cloud API connection, member push-down on enrollment, attendance webhook ingestion, differential sync only | New member enrolled in SaaS appears on eSSL device within 60 seconds |
| Weeks 34–35 | Cost control + access rules | Sync rate throttling per tier, per-device cost tracking in usage ledger, membership expiry gates access automatically | Expired member is denied access at turnstile within 5 minutes of expiry |

eSSL Cost Management (Critical)

eSSL ADMS cloud pricing scales with users and devices. At MVP scale (50 users, 2 devices), cost is ₹2,000/month. This is acceptable. At 500 users across 10 devices, cost reaches ₹10,000/month. Build the differential sync architecture now so you are not re-architecting this under scale pressure.

| Differential sync only | Never push full member lists. Push only new enrollments, plan changes, and terminations. |
| --- | --- |
| Scheduled sync windows | Non-critical data syncs (photo updates, plan name changes) batch to off-peak hours. |
| Per-device ledger tracking | Each eSSL device’s API call volume is tracked in the usage ledger for cost attribution. |
| Tier-based sync frequency | SMB tier: sync every 5 minutes. Growth tier: real-time push. Enterprise: dedicated device allocation. |

Exit Criteria

| EXIT | Device attendance updates in under 60 seconds. Expired member access denied within 5 minutes. eSSL costs are tracked per device and appear in usage ledger. Sync success rate above 99% over a 5-day test window. |
| --- | --- |

# 5. MVP Launch and First 90 Days GTM

| MVP LAUNCH Pilot Expansion + First Revenue | TIMELINE Weeks 36–39 | BUDGET ₹5L |
| --- | --- | --- |

## 5.1 What MVP Looks Like

By Week 35, your MVP includes: multi-tenant member management, UPI billing with GST invoicing, WhatsApp renewal automation, and eSSL biometric access control. This is a complete, sellable product for single-location commercial gyms.

## 5.2 First Revenue Targets

| Week 36–37 | Convert pilot gym to a paid plan (₹4,000–5,000/month Growth tier). First revenue milestone. |
| --- | --- |
| Week 37–38 | Close 2 additional gyms through personal outbound. Target: gym owners you met during pilot onboarding or IHFF. |
| Week 39+ | Target ₹1.5–2L MRR (₹30–40 paying gyms at average ₹4,500/month) as the Series A narrative trigger. |

## 5.3 IHFF Trade Show Strategy

IHFF Mumbai or Delhi is your highest-ROI single marketing spend. Timing your launch to coincide with the nearest IHFF cycle (typically September-October and February-March) is worth adjusting your roadmap for.

- Book the smallest available booth. You do not need square footage — you need a working demo.

- Bring one functioning eSSL biometric device. Let gym owners scan their own fingerprint and watch it appear in your dashboard in real time. This is your closing move.

- Collect business cards. Follow up via WhatsApp within 24 hours using a personalized message, not a broadcast template.

- Target quantity: 30 meaningful conversations, 10 demo bookings, 3 signed trials.

## 5.4 Reseller Channel (Start Early)

Contact biometric hardware distributors (eSSL resellers, turnstile suppliers) in Weeks 34-36, before your public launch. Offer them a simple arrangement: for every gym they refer that converts to a paid plan, they receive 20-30% of first-year contract value. These distributors are already walking into new gym fit-outs every week.

# 6. Risk Register

These are the 6 most likely execution risks for a solo founder on this budget. Each has a mitigation strategy you can execute without additional capital.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Contractor drops off mid-project | High | Critical | Milestone-based contracts with 2-week overlap buffer. Keep code in your repo, not theirs. Begin replacement sourcing at first sign of disengagement. |
| eSSL API changes or cost spike | Medium | High | Differential sync architecture limits API call volume from day one. Budget ₹2L contingency for licensing surprises. Track Cams API as fallback path. |
| WhatsApp template rejection | High | Medium | Pre-register 8 templates in Week 23. Maintain SMS as fallback. Never make a single template mission-critical for a launch demo. |
| Pilot gym churns before paying | Medium | High | Define success metrics with the pilot gym owner in Week 16. Get a signed letter of intent (not a contract) before Week 20. Their public testimonial is worth more than their ₹5,000/month plan. |
| Budget overrun (most likely in infra) | High | Medium | AWS cost alerts set at 80% of monthly budget from Week 1. Use RDS reserved instances after 2 months of stable usage. Review usage ledger monthly. |
| Slow sales cycle post-launch | Medium | High | Do not wait until Week 39 to sell. Begin outbound in Week 30 with a waitlist framing. Signed LOIs before launch close the first 5 gyms in Week 36. |

# 7. Master Timeline Summary

| Phase | Weeks | Key Milestone | Budget | Team State |
| --- | --- | --- | --- | --- |
| Phase 0 | 1–3 | All architecture + economics decisions locked | ₹1.2L | Founder only |
| Phase 1 | 4–9 | Secure multi-tenant skeleton deployed | ₹6.3L | Founder + 2 contractors |
| Phase 2 | 10–17 | Pilot gym live on production platform | ₹8.5L | Founder + 2 contractors |
| Phase 3 | 18–23 | UPI + GST billing live, pilot paying | ₹4.5L | Founder + 2 contractors |
| Phase 4 | 24–29 | WhatsApp renewal automation live | ₹4.8L | Founder + 2 contractors |
| Phase 5 | 30–35 | Biometric access control stable | ₹3.8L | Founder + 1 senior dev |
| MVP Launch | 36–39 | ₳1.5–2L MRR, 30+ paying gyms pipeline | ₹5L | Founder + sales hiring begins |

## Your Week 1 Action List

Stop planning. Start these five things today:

- Post the senior full-stack developer job spec on LinkedIn and Toptal today.

- Begin the BSP selection matrix with WAPI and AiSensy as your first two evaluations.

- Register a private limited company or LLP if not done. Apply for GST registration simultaneously.

- Open a conversation with one gym owner you already know. Offer 3 months free for pilot access.

- Create the AWS account. Set a billing alert at ₹25,000/month from day one.

The plan is done. The window is open. Build it.